## Millicom KT Tracker
# | KT - Environment | Activities/Tasks | Trainer | Comment | Knowledge Recepient Name | Project Allocation Date | Planned Duration | Planned Start Date | Planned End Date | KT Completed | Reverse KT Taken By | Reverse KT completed | Performance Metrics
1 | Overview | About client and project overview |  |  |  | 2025-09-30 | 1day | 2025-10-10 | 2025-10-10
2 | Hexaware Support - An overview | Level of support |  |  |  | 2025-09-30 | 1day | 2025-11-11 | 2025-11-11
|  | Support Coverage |  |  |  | 2025-09-30 | 1day | 2025-11-11 | 2025-11-11
|  | Mode of support |  |  |  | 2025-09-30 | 1day | 2025-11-11 | 2025-11-11
|  | Shift roaster/timings |  |  |  | 2025-09-30 | 1day | 2025-11-11 | 2025-11-11
|  | Off hour support/Holiday support |  |  |  | 2025-09-30 | 1day | 2025-11-11 | 2025-11-11
3 | Scope of Support | In Scope |  |  |  | 2025-09-30 | 1day | 2025-11-12 | 2025-11-12
|  | Out of Scope |  |  |  | 2025-09-30 | 1day | 2025-11-12 | 2025-11-12
4 | Project Access | Access to sharepoint Documents |  |  |  | 2025-09-30 | 7days | 2025-10-24 | 2025-10-31
|  | Backoffice account (UAT, Prod) |  |  |  | 2025-09-30 | 7days | 2025-10-24 | 2025-10-31
|  | Millicom - JIRA |  |  |  | 2025-09-30 | 7days | 2025-10-24 | 2025-10-31
|  | AWS Single Sign-On (Payment Gateway AWS Prod & Non-Prod, TIGO AWS Prod & Non- Prod, TigoID Manager and GitLab) |  |  |  | 2025-09-30 | 7days | 2025-10-24 | 2025-10-31
|  | GitLab (digital-channels / master-account-record, digital-channels / Millicom_Back_Office,digital-channels / Millicom_IaC,digital-channels / Millicom_Payment_Helpers, digital-channels / Millicom_Server,digital-channels / payment-gateway-afs,digital-channels / tigo-id) |  |  |  | 2025-09-30 | 7days | 2025-10-24 | 2025-10-31
|  | KPI Dashboard |  |  |  | 2025-09-30 | 7days | 2025-10-24 | 2025-10-31
|  | Status check for PayU Processor Application |  |  |  | 2025-09-30 | 7days | 2025-10-24 | 2025-10-31
|  | Alarm & Ticket Notification to Hexaware ID (mob-support-alarms@mobiquityinc.com to receive AWS Alarm Notification & mob-support@mobiquityinc.com to receive JIRA ticket notification) |  |  |  | 2025-09-30 | 7days | 2025-10-24 | 2025-10-31
|  | VPN Access (Global Protect should have all US Gateway) |  |  |  | 2025-09-30 | 7days | 2025-10-24 | 2025-10-31
|  | Client Teams Access (mobiquity-support & General) |  |  |  | 2025-09-30 | 7days | 2025-10-24 | 2025-10-31
5 | SLAs | Priority levels |  |  |  | 2025-09-30 | 1day | 2025-10-14 | 2025-10-14
|  | Response time SLA |  |  |  | 2025-09-30 | 1day | 2025-10-14 | 2025-10-14
|  | Resolution time SLA |  |  |  | 2025-09-30 | 1day | 2025-10-14 | 2025-10-14
6 | Team Org structure | Millicom Support Team | Pradeep D |  |  | 2025-09-30 | 1day | 2025-10-13 | 2025-10-13
|  | Mob Support Team | Pradeep D |  |  | 2025-09-30 | 1day | 2025-10-13 | 2025-10-13
|  | App Support Team | Pradeep D |  |  | 2025-09-30 | 1day | 2025-10-13 | 2025-10-13
|  | L3 team | Pradeep D |  |  | 2025-09-30 | 1day | 2025-10-13 | 2025-10-13
7 | Ticketing Tool(Mention respective tool)- An overview | Millicom Jira Ticketing tool |  |  |  | 2025-09-30 | 1day | 2025-10-10 | 2025-10-10
8 | Application Overview | MiTigo (OneApp) (Features, Performance Monitoring) |  |  |  | 2025-09-30 | 1day | 2025-10-09 | 2025-10-09
|  | TigoId (DAR) (AWS Architecture, Dashboard Monitoring and Analysis) | Venesh G | Dashboards Understanding | Sadhu Rajesh | 2025-09-30 | 2days | 2025-10-07 | 2025-10-09 | Progress | - | - | -
|  | Payment Gateway (AWS Architecture, Dashboard Monitoring and Analysis) | Venesh G | Dashboards Understanding | Sadhu Rajesh | 2025-09-30 | 2days | 2025-10-07 | 2025-10-09 | Progress | - | - | -
|  | Payment Gateway - Backoffice | Pradeep D |  |  | 2025-09-30 | 1day | 2025-10-08 | 2025-10-08
|  | TigoID Manager / Cognito | Pradeep D |  |  | 2025-09-30 | 2days | 2025-10-08 | 2025-10-09
9 | Incident Management | Workflow Process |  |  |  | 2025-09-30 | 1day | 2025-10-10 | 2025-10-10
|  | Types of Incident |  |  |  | 2025-09-30 | 1day | 2025-10-10 | 2025-10-10
|  | Incident opening/Assignment/Transfer/Closing |  |  |  | 2025-09-30 | 1day | 2025-10-10 | 2025-10-10
10 | Live Session on Issues and Jira incidents | Analysing API gateway 4xx and 5xx errors |  |  |  | 2025-09-30 | 1day | 2025-10-15 | 2025-10-15
|  | Analysing Lambda errors |  |  |  | 2025-09-30 | 1day | 2025-10-15 | 2025-10-15
|  | Analysing Billing system API errors in Lambda |  |  |  | 2025-09-30 | 1day | 2025-10-16 | 2025-10-16
|  | Back office KT |  |  |  | 2025-09-30 | 1day | 2025-10-16 | 2025-10-16
|  | Analysing spike in CPU, Read and Write IOPs in RDS instance |  |  |  | 2025-09-30 | 1day | 2025-10-17 | 2025-10-17
|  | Analysing Slow query logs in RDS instance |  |  |  | 2025-09-30 | 1day | 2025-10-17 | 2025-10-17
|  | Analysing Kinesis Data Stream API Timeout errors |  |  |  | 2025-09-30 | 1day | 2025-10-21 | 2025-10-21
|  | Analysing Analytics Alarms & OTP Alarm with it's priority. |  |  |  | 2025-09-30 | 1day | 2025-10-21 | 2025-10-21
|  | Investigationg Payment Gateway AFS Alarm Notification |  |  |  | 2025-09-30 | 1day | 2025-10-22 | 2025-10-22
|  | Differentiation of Cognito throttle & Lambda Throttle and it's procedure |  |  |  | 2025-09-30 | 1day | 2025-10-22 | 2025-10-22
|  | Invoking API calls to generate Enrollments reports |  |  |  | 2025-09-30 | 1day | 2025-10-23 | 2025-10-23
|  | Building cloudwatch insights query to analyse the errors logs from lambda, API gateway and RDS logs |  |  |  | 2025-09-30 | 1day | 2025-10-23 | 2025-10-23
|  | Purging SQS queues |  |  |  | 2025-09-30 | 1day | 2025-10-24 | 2025-10-24
[6 empty] | 2025-09-30 | 1day | 2025-10-24 | 2025-10-24
11 | Tools | Day to day operations |  |  |  | 2025-09-30 | 1day | 2025-10-27 | 2025-10-27
12 | Reports | Shift Handover |  |  |  | 2025-09-30 | 1day | 2025-10-27 | 2025-10-27
|  | COVID Report/Daily Status Report (DSR) |  |  |  | 2025-09-30 | 1day | 2025-10-28 | 2025-10-28
|  | Weekly Status Report (WSR) |  |  |  | 2025-09-30 | 1day | 2025-10-28 | 2025-10-28
|  | Monthly Status Report (MSR) |  |  |  | 2025-09-30 | 2days | 2025-10-29 | 2025-10-30
|  | Master Tracker Sheet |  |  |  | 2025-09-30 | 1day | 2025-10-27 | 2025-10-27
|  | Bi-Weekly Presentation |  |  |  | 2025-09-30 | 2days | 2025-10-31 | 2025-11-03
|  | Action Tracker |  |  |  | 2025-09-30 | 1day | 2025-11-04 | 2025-11-04
|  | MOM (Minutes Of Meeting) document |  |  |  | 2025-09-30 | 1day | 2025-11-04 | 2025-11-04
|  | Alarm Raised Sheet |  |  |  | 2025-09-30 | 1day | 2025-11-05 | 2025-11-05
|  | Alarm Tuning Activities |  |  |  | 2025-09-30 | 1day | 2025-11-05 | 2025-11-05
13 | Contacts | Hexaware Contacts |  |  |  | 2025-09-30 | 1day | 2025-11-06 | 2025-11-06
|  | Contacts |  |  |  | 2025-09-30 | 1day | 2025-11-06 | 2025-11-06
14 | Escalation Matrix | Hexaware Escalation |  |  |  | 2025-09-30 | 1day | 2025-11-06 | 2025-11-06
|  | Mobiquity Escalation (Vertical Team Members) |  |  |  | 2025-09-30 | 1day | 2025-11-06 | 2025-11-06
15 | Regular Activities | Turn Over/Shift Handover |  |  |  | 2025-09-30 | 1day | 2025-11-07 | 2025-11-07
|  | Weekly Status Meeting |  |  |  | 2025-09-30 | 1day | 2025-11-07 | 2025-11-07
|  | Daily Team Huddle |  |  |  | 2025-09-30 | 1day | 2025-11-07 | 2025-11-07
|  | Gap Analysis Call (Weekly twice with Scrum Master, L2 & L3 Team) |  |  |  | 2025-09-30 | 1day | 2025-11-10 | 2025-11-10
|  | KT Call (Fort-Nightly call with L3 Team - Tuesday with DAR & Wednesday with PG) |  |  |  | 2025-09-30 | 1day | 2025-11-10 | 2025-11-10
|  | Bi-Weekly Team Meeting (Colloaboration with L2 & L3 Team Members) |  |  |  | 2025-09-30 | 1day | 2025-11-10 | 2025-11-10
16 | Work Ethics | Sign in/off procedure |  |  |  | 2025-09-30 | 1day | 2025-11-14 | 2025-11-14
|  | Turn over procedure |  |  |  | 2025-09-30 | 1day | 2025-11-14 | 2025-11-14
|  | Non-Disclosure Agreement |  |  |  | 2025-09-30 | 1day | 2025-11-14 | 2025-11-14
|  | Account expiry renewal |  |  |  | 2025-09-30 | 1day | 2025-11-14 | 2025-11-14