## Sheet1
Ref | Assignment group->Full name | Assigned to->Full name | Short description | Caller->Full name | Priority | Status | Issue start date | Last update
TID-2681 | TTC_ITO_DIGITAL_NOCL1.5 | solano.torales | DAR 4XX Errors on 20th, 21st July 2022 | mob-support | Major | Ready For Dev | 2022-07-22 23:15 | 2022-11-30 00:41
TID-2680 | TTC_ITO_DIGITAL_L3_DAR | dany.vasquez | DAR API - Reduce 4XX errors caused by missing validations | mob-support | Major | Backlog | 2022-04-04 13:06 | 2022-09-06 18:59
PAYMENTGATE-8163 | TTC_ITO_DIGITAL_NOCL1.5 | azelayandia | Release - Cambio de Fulfillment de V3 a V1 Mi Tigo GT | mob-support | Critical | To Do | 2026-02-20 08:53 | 2026-07-01 08:36
PAYMENTGATE-8162 | TTC_ITO_DIGITAL_NOCL1.5 | azelayandia | Testing - Cambio de Fulfillment de V3 a V1 Mi Tigo GT | mob-support | Critical | To Do | 2026-02-20 08:53 | 2026-07-01 08:36
DIGSUPPORT-20100 | TTC_ITO_DIGITAL_L3_PAYMENTGATEWAY | ShalinS | PaymentGateway-prod-Token-Worker-Exceptions¦java.lang.NullPointerException: null | pradeepd1 | Medium | Escalated | 2026-05-08 04:43 | 2026-05-12 14:48
DIGSUPPORT-19502 | TTC_ITO_DIGITAL_L2_PAYMENTGATEWAY | mob-support | Alarm Tuning-PaymentGateway-Private-prod-API-InsufficientCount | mob-support | Low | Waiting for support | 2026-03-27 16:52 | 2026-05-16 03:36
DIGSUPPORT-19501 | TTC_ITO_DIGITAL_L2_PAYMENTGATEWAY | mob-support | Configuration - Threshold change-PaymentGateway-prod-API-OrdersCount | mob-support | Low | To Do | 2026-03-27 15:58 | 2026-07-01 08:53
DIGSUPPORT-19500 | TTC_ITO_DIGITAL_L2_PAYMENTGATEWAY | mob-support | Threshold change-PaymentGateway-prod-API-OrdersCount | mob-support | Low | To Do | 2026-03-27 15:58 | 2026-07-01 08:53
DIGSUPPORT-19479 | TTC_ITO_DIGITAL_NOCL1.5 | app.support | PaymentGateway-prod-AsyncPayments-PaymentStatus-Poller-Exceptions¦QRM Payment Processor | SadhuR | Medium | Escalated | 2026-03-26 16:39 | 2026-06-24 17:41
DIGSUPPORT-19154 | TTC_ITO_DIGITAL_L3_PAYMENTGATEWAY | kvalsangkar | PaymentGateway-prod-Event-Message-Processor-Exceptions ¦ Could not initialize class software.amazon.awssdk.crt.io.ClientBootstrap | mob-support | Medium | Escalated | 2026-03-06 10:33 | 2026-03-06 11:36
DIGSUPPORT-18100 | TTC_ITO_DIGITAL_L3_PAYMENTGATEWAY | kvalsangkar | PaymentGateway-prod-AsyncPayments-Microservice-Exceptions¦QueryTimeoutException | pradeepd1 | Medium | Escalated | 2026-01-09 02:07 | 2026-05-20 00:24
DIGSUPPORT-18006 | TTC_ITO_DIGITAL_L3_DAR | dany.vasquez | tigo-cognito-prod-master-Monitoring-6I7LSTA3KZJH-DARApiGateway4XXErrorAlarm-1RU6CTB3HN9ZJ¦/v4/public/auth/login/ott | pradeepd1 | Medium | Escalated | 2026-01-02 05:22 | 2026-06-04 05:42
DIGSUPPORT-17977 | TTC_ITO_DIGITAL_L3_PAYMENTGATEWAY | kvalsangkar | PaymentGateway-prod-arc-RDS-cluster-writer-CPUUtilization-Manual | pradeepd1 | Medium | Escalated | 2025-12-30 05:21 | 2026-01-09 22:55
DIGSUPPORT-17815 | TTC_ITO_DIGITAL_L3_PAYMENTGATEWAY | kvalsangkar | PaymentGateway-prod-RDS-cluster-reader-CPUUtilization-Manual | veneshg | Medium | Escalated | 2025-12-17 19:28 | 2026-05-20 12:19
DIGSUPPORT-16579 | TTC_ITO_DIGITAL_L3_PAYMENTGATEWAY | pthakur | PaymentGateway-prod-Event-Message-Processor-Exceptions¦ java.lang.NullPointerException | pradeepd1 | Medium | Escalated | 2025-10-08 21:25 | 2025-10-10 17:47
DIGSUPPORT-16547 | TTC_ITO_DIGITAL_L3_PAYMENTGATEWAY | pthakur | PaymentGateway-prod-RP-Scheduler-Batch-Creator-Exceptions¦ Duplicate Batch file name | pradeepd1 | Medium | Escalated | 2025-10-06 23:24 | 2025-10-08 00:09
DIGSUPPORT-16543 | TTC_ITO_DIGITAL_L3_PAYMENTGATEWAY | pthakur | PaymentGateway-prod-RDS-VolumeWriteIOPs | pradeepd1 | Medium | Escalated | 2025-10-06 20:22 | 2025-10-06 22:58
DIGSUPPORT-16480 | TTC_ITO_DIGITAL_L3_PAYMENTGATEWAY | pthakur | PaymentGateway-AFS-prod-es-ClusterFreeStorageSpaceTooLowAlarm | pradeepd1 | Medium | Escalated | 2025-10-02 09:19 | 2025-11-03 09:14
DIGSUPPORT-16346 | TTC_ITO_DIGITAL_L3_PAYMENTGATEWAY | ShalinS | PaymentGateway-prod-AsyncPendingTokens-Identifier-Exceptions¦Timeout | pradeepd1 | Medium | Escalated | 2025-09-24 20:06 | 2026-05-06 06:53
DIGSUPPORT-16277 | TTC_ITO_DIGITAL_L3_PAYMENTGATEWAY | pthakur | PaymentGateway-prod-AsyncPayments-Microservice-Exceptions¦400¦Invalid Request | pradeepd1 | Medium | Escalated | 2025-09-20 01:08 | 2025-12-19 00:45
DIGSUPPORT-16176 | TTC_ITO_DIGITAL_L3_PAYMENTGATEWAY | schavan | Alarm Tuning-PaymentGateway-prod-API-OrdersCount | manojk25 | Low | Escalated | 2025-09-14 15:02 | 2026-01-23 23:00
DIGSUPPORT-16117 | TTC_ITO_DIGITAL_L3_PAYMENTGATEWAY | kvalsangkar | PaymentGateway-> Multiple Lambda Exceptions ¦ Communications link failure | veneshg | Medium | Escalated | 2025-09-11 21:11 | 2026-05-20 12:06
DIGSUPPORT-16107 | TTC_ITO_DIGITAL_L3_PAYMENTGATEWAY | kvalsangkar | PaymentGateway-> Multiple Lambda-Worker-Exceptions¦java.lang.NullPointerException | pradeepd1 | Medium | Escalated | 2025-09-11 12:37 | 2026-05-14 04:43
DIGSUPPORT-16085 | TTC_ITO_DIGITAL_L3_PAYMENTGATEWAY | pthakur | PaymentGateway-AFS-prod-Transactiondata-firehose-ElasticsearchDataFreshness | tetalik | Medium | Escalated | 2025-09-10 15:45 | 2025-12-01 01:49
DIGSUPPORT-16065 | TTC_ITO_DIGITAL_L3_PAYMENTGATEWAY | roman.pinango.g | PaymentGateway-prod-Payment-Token-Microservice-Exceptions¦Invalid Request¦400 | pradeepd1 | Medium | Escalated | 2025-09-09 11:06 | 2025-10-14 23:08
DIGSUPPORT-16030 | TTC_ITO_DIGITAL_L3_PAYMENTGATEWAY | roman.pinango.g | PaymentGateway-prod-API-5XXErrors¦Payment Processor - Nequi¦Http Response Status of Nequi Payment API: 200 | senthilkumar1 | Medium | Escalated | 2025-09-06 21:17 | 2025-09-16 15:28
DIGSUPPORT-16015 | TTC_ITO_DIGITAL_L3_PAYMENTGATEWAY | pthakur | PaymentGateway-prod-Event-Message-Processor-Exceptions¦500 HTTP Status Code | manojk25 | Medium | Escalated | 2025-09-05 16:00 | 2025-09-05 16:19
DIGSUPPORT-15895 | TTC_ITO_DIGITAL_L3_PAYMENTGATEWAY | kvalsangkar | PaymentGateway-prod-API-5XXErrors¦QRM Payment processor¦Duplicate entry with Primary Key | veneshg | Medium | Escalated | 2025-08-29 22:43 | 2025-10-13 21:21
DIGSUPPORT-15752 | TTC_ITO_DIGITAL_L3_PAYMENTGATEWAY | schavan | PaymentGateway-prod-RDS-ActiveTransactions | veneshg | Medium | Escalated | 2025-08-20 21:20 | 2026-05-08 02:08
DIGSUPPORT-15183 | TTC_ITO_DIGITAL_L3_DAR | dany.vasquez | tigo-cognito-prod-master-Monitoring-6I7LSTA3KZJH-DARApiGateway5XXErrorAlarm-13T4WI2OP8WG1¦TRUSTED-API:SYNC_BY_DOCUMENT_FAILED | pradeepd1 | Medium | In Resolution | 2025-07-13 23:07 | 2026-05-16 02:35
DIGSUPPORT-15157 | TTC_ITO_DIGITAL_L3_PAYMENTGATEWAY | pthakur | PaymentGateway-prod-Payment-Token-Microservice-Exceptions¦ java.net.SocketTimeoutException: timeout | pradeepd1 | Medium | Escalated | 2025-07-11 20:44 | 2025-08-28 18:24
DIGSUPPORT-14886 | TTC_ITO_DIGITAL_L3_DAR | dany.vasquez | tigo-cognito-prod-master-Monitoring-6I7LSTA3KZJH-DARApiGateway4XXErrorAlarm-1RU6CTB3HN9ZJ¦POST:/v4/public/oauth2/token¦refresh token not found | veneshg | Medium | Escalated | 2025-07-01 10:16 | 2026-06-26 19:57
DIGSUPPORT-14721 | TTC_ITO_DIGITAL_L3_PAYMENTGATEWAY | pthakur | PaymentGateway-prod-Subscription-Batch-Creator-Processor-Exceptions¦Task timed out | pradeepd1 | Medium | Escalated | 2025-06-22 07:56 | 2025-06-23 10:25
DIGSUPPORT-14615 | TTC_ITO_DIGITAL_L3_PAYMENTGATEWAY | pthakur | PaymentGateway-prod-API-4XXErrors¦Invalid Request | pradeepd1 | Medium | Escalated | 2025-06-17 22:51 | 2025-06-18 00:06
DIGSUPPORT-14069 | TTC_ITO_DIGITAL_L3_PAYMENTGATEWAY | pthakur | PaymentGateway-AFS-prod-Rule-Engine-Processor-Errors | AnandM4 | Medium | Escalated | 2025-05-16 10:35 | 2025-08-28 01:09
DIGSUPPORT-13944 | TTC_ITO_DIGITAL_L3_PAYMENTGATEWAY | pthakur | PaymentGateway-prod-Delete-Payment-Tokens-Processor-Exceptions¦Error in deleting profile at CyberSource | pradeepd1 | Medium | Escalated | 2025-05-13 12:04 | 2025-05-13 12:20
DIGSUPPORT-13713 | TTC_ITO_DIGITAL_L3_PAYMENTGATEWAY | pthakur | PaymentGateway-prod-Multiple-Fulfillment-Record-Processor-Throttles | pradeepd1 | Medium | Escalated | 2025-04-29 17:06 | 2025-05-04 23:59
DIGSUPPORT-13468 | TTC_ITO_DIGITAL_L3_PAYMENTGATEWAY | pthakur | PaymentGateway-prod-Enrollment-Microservice-Exceptions¦Failed to connect to prod.api.tigo.com | pradeepd1 | Medium | Escalated | 2025-04-13 23:17 | 2025-04-13 23:58
DIGSUPPORT-13466 | TTC_ITO_DIGITAL_L3_PAYMENTGATEWAY | pthakur | PaymentGateway-prod-Enrollment-Microservice-Exceptions¦ ConstraintViolationException: Duplicate entry | pradeepd1 | Medium | Escalated | 2025-04-13 22:53 | 2025-07-17 21:05
DIGSUPPORT-13235 | TTC_ITO_DIGITAL_L3_PAYMENTGATEWAY | kvalsangkar | Alarm Tuning-PaymentGateway-prod-Enrollment-Microservice-Exceptions | manojk25 | Medium | Escalated | 2025-04-02 18:43 | 2026-01-28 17:21
DIGSUPPORT-12767 | TTC_ITO_DIGITAL_L3_PAYMENTGATEWAY | pthakur | PaymentGateway-prod-AsyncPayments-PaymentStatus-Poller-Timeout¦ java.net.SocketTimeoutException: timeout | pradeepd1 | Medium | Escalated | 2025-03-11 20:45 | 2025-03-11 23:58
DIGSUPPORT-12743 | TTC_ITO_DIGITAL_L3_PAYMENTGATEWAY | kvalsangkar | Alarm Tuning-PaymentGateway-prod-RDS-DeleteLatency | mob-support | Low | Escalated | 2025-03-10 23:54 | 2026-01-28 17:28
DIGSUPPORT-12730 | TTC_ITO_DIGITAL_L3_PAYMENTGATEWAY | kvalsangkar | Alarm Tuning-PaymentGateway-prod-RDS-UpdateLatency | mob-support | Low | Escalated | 2025-03-10 17:53 | 2026-01-28 17:29
DIGSUPPORT-12626 | TTC_ITO_DIGITAL_L3_PAYMENTGATEWAY | pthakur | PaymentGateway-prod-Enrollment-Microservice-Exceptions¦Duplicate entry | pradeepd1 | Medium | Escalated | 2025-03-05 21:02 | 2025-03-06 11:52
DIGSUPPORT-12402 | TTC_ITO_DIGITAL_L3_PAYMENTGATEWAY | pthakur | PaymentGateway-prod-AsyncPayments-PaymentStatus-Poller-Exceptions¦Task timed Out | AnandM4 | Medium | Escalated | 2025-02-20 12:22 | 2025-02-21 01:50
DIGSUPPORT-12401 | TTC_ITO_DIGITAL_L3_PAYMENTGATEWAY | pthakur | PaymentGateway-prod-API-5XXErrors¦PaymentGateway-prod-Payment-Token-Microservice¦ API gateway timeout | honeyp | Medium | Escalated | 2025-02-20 11:51 | 2025-02-20 14:10
DIGSUPPORT-12293 | TTC_ITO_DIGITAL_L3_PAYMENTGATEWAY | pthakur | PaymentGateway-prod-AuthReversal-Worker-Exceptions | pradeepd1 | Medium | Escalated | 2025-02-14 20:58 | 2025-02-14 23:12
DIGSUPPORT-12274 | TTC_ITO_DIGITAL_L3_PAYMENTGATEWAY | pthakur | PaymentGateway-prod-Refund-Worker-Exceptions¦WompiBancolombia Processor does not support 'Refund' method | pradeepd1 | Medium | Escalated | 2025-02-13 15:50 | 2025-05-25 23:42
DIGSUPPORT-12020 | TTC_ITO_DIGITAL_L3_PAYMENTGATEWAY | pthakur | PaymentGateway-prod-Transactions-Microservice-Exceptions¦Querytimeoutexception | pradeepd1 | Medium | Escalated | 2025-01-30 19:35 | 2025-01-30 22:19
DIGSUPPORT-11826 | TTC_ITO_DIGITAL_L3_PAYMENTGATEWAY | pthakur | PaymentGateway-prod-Transactions-Microservice-Exceptions¦Querytimeoutexception | pradeepd1 | Medium | Escalated | 2025-01-16 22:24 | 2025-01-16 23:48
DIGSUPPORT-11551 | TTC_ITO_DIGITAL_L3_PAYMENTGATEWAY | pthakur | PaymentGateway-prod-Fulfillment-Worker-Exceptions¦ java.lang.NullPointerException | pradeepd1 | Medium | Escalated | 2024-12-26 19:16 | 2025-07-14 23:51
DIGSUPPORT-11078 | TTC_ITO_DIGITAL_L3_PAYMENTGATEWAY | pthakur | PaymentGateway-prod-RPBatchItemsPayment-Processor-Exceptions¦java.lang.NullPointerException: null | pradeepd1 | Medium | Escalated | 2024-11-27 18:59 | 2026-05-21 03:36
DIGSUPPORT-10998 | TTC_ITO_DIGITAL_L3_PAYMENTGATEWAY | pthakur | PaymentGateway-prod-API-5XXErrors¦PaymentGateway-prod-Payment-Token-Microservice¦Error while getting Nequi token | honeyp | Medium | Escalated | 2024-11-22 13:22 | 2024-11-22 14:23
DIGSUPPORT-10686 | TTC_ITO_DIGITAL_L3_DAR | dany.vasquez | tigo-cognito-prod-master-Monitoring-6I7LSTA3KZJH-DARApiGateway5XXErrorAlarm-13T4WI2OP8WG1¦/v4/public/auth/login/phone/he¦SequelizeUniqueConstraintError | pradeepd1 | Medium | Escalated | 2024-11-08 02:26 | 2026-06-19 20:34
DIGSUPPORT-10110 | TTC_ITO_DIGITAL_L3_PAYMENTGATEWAY | pthakur | PaymentGateway-prod-RDS-Queries | pradeepd1 | Medium | Escalated | 2024-10-04 20:04 | 2024-10-04 20:44
DIGSUPPORT-10108 | TTC_ITO_DIGITAL_L3_PAYMENTGATEWAY | pthakur | PaymentGateway-prod-RPBatchItems-Processor-Exceptions¦java.lang.NullPointerException: null | HeerabJ | Medium | Escalated | 2024-10-04 18:36 | 2026-05-21 03:37
DIGSUPPORT-10060 | TTC_ITO_DIGITAL_L3_PAYMENTGATEWAY | pthakur | PaymentGateway-prod-Token-Worker-Exceptions¦Duplicate entry | pradeepd1 | Medium | Escalated | 2024-10-02 11:55 | 2025-01-03 00:45
DIGSUPPORT-7900 | TTC_ITO_DIGITAL_NOCL1.5 | rolando.romero | paymentgateway-base-config-prod-stack-IAMPolicyChangesAlarm-T1PD7XV5K9BQ | mustafam | Medium | Escalated | 2024-05-29 00:26 | 2024-10-31 06:47
DIGSUPPORT-5751 | TTC_ITO_DIGITAL_NOCL1.5 | rolando.romero | tigo-cognito-tigoid-prod-base-UnauthorizedAPICallsAlarm-1XGEUVQ5OP4G7 | mob-support | Medium | Escalated | 2024-02-03 13:25 | 2025-05-29 02:32
DIGSUPPORT-5703 | TTC_ITO_DIGITAL_NOCL1.5 | rolando.romero | tigo-cognito-tigoid-prod-base-UnauthorizedAPICallsAlarm-1XGEUVQ5OP4G7 | mob-support | Medium | Escalated | 2024-02-01 12:08 | 2025-05-29 02:29
DIGSUPPORT-5258 | TTC_ITO_DIGITAL_L3_PAYMENTGATEWAY | kvalsangkar | PaymentGateway-prod-Event-Message-Processor-Exceptions¦ Task timed out-Processing event message | mob-support | Medium | Escalated | 2024-01-11 13:12 | 2026-05-21 02:52
I-079104 | TTC_ITO_DIGITAL_L3_PAYMENTGATEWAY |  | PaymentGateway-prod-arc-RDS-cluster-reader-CPUUtilization-Manual | pradeepd1 hexaware | Medium | In Progress | 2026-08-14 01:00 | 2026-08-14 06:18
I-078843 | TTC_ITO_DIGITAL_NOCL1.5 |  | tigo-cognito-prod-master-Monitoring-6I7LSTA3KZJH-DARApiGateway5XXErrorAlarm-13T4WI2OP8WG1¦EXTERNAL-APIS:BILLING-SYSTEM-GET-ACCOUNTS-API-TIMEOUT¦Billing system get accounts api timed out. | SadhuR hexaware | Medium | In Progress | 2026-08-13 12:16 | 2026-08-13 12:48
I-078720 | TTC_ITO_DIGITAL_L2_PAYMENTGATEWAY |  | PaymentGateway-prod-RDS-Queries | pradeepd1 hexaware | Medium | In Progress | 2026-08-12 19:00 | 2026-08-13 12:50
I-078664 | TTC_ITO_DIGITAL_NOCL1.5 |  | tigo-cognito-prod-master-Monitoring-6I7LSTA3KZJH-BillingSystemGetAccountsAPITimeoutErrorAlarm-1PCEMSDTPMP30 | Pammi Reddy | Medium | In Progress | 2026-08-09 13:30 | 2026-08-13 04:11
I-078372 | TTC_ITO_DIGITAL_L3_PAYMENTGATEWAY |  | PaymentGateway-prod-Token-Worker-Exceptions¦java.lang.NullPointerException: null | pradeepd1 hexaware | Medium | In Progress | 2026-08-11 19:00 | 2026-08-12 11:30
I-078273 | TTC_ITO_DIGITAL_NOCL1.5 |  | PaymentGateway-prod-API-5XXErrors | Pammi Reddy | Medium | In Progress | 2026-08-11 00:30 | 2026-08-12 02:11
I-078079 | TTC_ITO_DIGITAL_NOCL1.5 |  | tigo-cognito-prod-master-Monitoring-6I7LSTA3KZJH-DARApiGateway5XXErrorAlarm-13T4WI2OP8WG1¦EXTERNAL-APIS:BILLING-SYSTEM-GET-ACCOUNTS-API-RETURNED-INTERNAL-SERVER-ERROR¦HE-OTP-LOGIN:ERR79 | SadhuR hexaware | Medium | In Progress | 2026-08-11 12:11 | 2026-08-11 13:12
I-077937 | TTC_ITO_DIGITAL_L3_DAR |  | tigo-cognito-prod-master-Monitoring-6I7LSTA3KZJH-DARApiGateway5XXErrorAlarm-13T4WI2OP8WG1 | pradeepd1 hexaware | Medium | In Progress | 2026-08-10 19:00 | 2026-08-11 09:23
I-077133 | TTC_ITO_DIGITAL_L3_PAYMENTGATEWAY |  | PaymentGateway-prod-Enrollment-Microservice-Exceptions | Pammi Reddy | Medium | In Progress | 2026-08-07 05:43 | 2026-08-07 06:33
I-076635 | TTC_ITO_DIGITAL_L3_DAR |  | tigo-cognito-prod-master-Monitoring-6I7LSTA3KZJH-LambdaThrottles-T4BHZQAJD6PY | pradeepd1 hexaware | Medium | In Progress | 2026-08-04 19:00 | 2026-08-05 16:38
I-076490 | TTC_ITO_DIGITAL_NOCL1.5 |  | tigo-cognito-prod-master-Monitoring-6I7LSTA3KZJH-OtpApiGateway4XXErrorAlarm-KCC0X1UFXS1F¦V2-PHONE-OTP:INCORRECT-OTP | SadhuR hexaware | Medium | In Progress | 2026-08-05 | 2026-08-05 06:27
I-075717 | TTC_ITO_DIGITAL_NOCL1.5 |  | tigo-cognito-prod-master-Monitoring-6I7LSTA3KZJH-BillingSystemGetAccountsAPITimeoutErrorAlarm-1PCEMSDTPMP30¦EXTERNAL-APIS:BILLING-SYSTEM-GET-ACCOUNTS-API-TIMEOUT | SadhuR hexaware | Medium | In Progress | 2026-08-03 | 2026-08-04 18:11
I-074517 | TTC_ITO_DIGITAL_NOCL1.5 |  | tigo-cognito-prod-master-Monitoring-6I7LSTA3KZJH-BillingSystemGetAccountsAPITimeoutErrorAlarm-1PCEMSDTPMP30¦EXTERNAL-APIS:BILLING-SYSTEM-GET-ACCOUNTS-API-TIMEOUT | SadhuR hexaware | Medium | In Progress | 2026-07-29 19:05 | 2026-08-04 18:12
I-073685 | TTC_ITO_DIGITAL_NOCL1.5 |  | PaymentGateway-prod-API-5XXErrors | veneshg hexaware | Medium | In Progress | 2026-07-28 04:18 | 2026-08-04 18:14
I-073618 | TTC_ITO_DIGITAL_NOCL1.5 |  | tigo-cognito-prod-master-Monitoring-6I7LSTA3KZJH-DARApiGateway5XXErrorAlarm-13T4WI2OP8WG1¦EXTERNAL-APIS:BILLING-SYSTEM-GET-ACCOUNTS-API-TIMEOUT | SadhuR hexaware | Medium | In Progress | 2026-07-27 12:30 | 2026-08-04 18:16
I-073218 | TTC_ITO_DIGITAL_L3_DAR |  | tigo-cognito-prod-master-Monitoring-6I7LSTA3KZJH-DARApiGateway5XXErrorAlarm-13T4WI2OP8WG1 | pradeepd1 hexaware | Medium | In Progress | 2026-07-23 19:00 | 2026-07-27 14:14
I-072666 | TTC_ITO_DIGITAL_NOCL1.5 |  | tigo-cognito-prod-master-Monitoring-6I7LSTA3KZJH-DARApiGateway5XXErrorAlarm-13T4WI2OP8WG1¦EXTERNAL-APIS:BILLING-SYSTEM-GET-ACCOUNTS-API-RETURNED-INTERNAL-SERVER-ERROR | SadhuR hexaware | Medium | In Progress | 2026-07-23 02:50 | 2026-08-04 18:17
I-072407 | TTC_ITO_DIGITAL_NOCL1.5 |  | PaymentGateway-prod-API-5XXErrors | TetaliK hexaware | Medium | In Progress | 2026-07-21 21:33 | 2026-08-05 12:30
I-071975 | TTC_ITO_DIGITAL_NOCL1.5 |  | tigo-cognito-prod-master-MonitoringOTP-UI11ZHWWG91S-ExternalKannelSendSMSApiFailedCOAlarm-1V16AQ48LJ175 | veneshg hexaware | Medium | In Progress | 2026-07-21 22:20 | 2026-08-05 12:31
I-071532 | TTC_ITO_DIGITAL_NOCL1.5 |  | PaymentGateway-prod-API-5XXErrors¦Nequi and FRI | SadhuR hexaware | Medium | In Progress | 2026-07-19 16:20 | 2026-08-05 12:32
I-071331 | TTC_ITO_DIGITAL_L3_DAR |  | tigo-cognito-prod-master-Monitoring-6I7LSTA3KZJH-DARApiGateway4XXErrorAlarm-1RU6CTB3HN9ZJ | pradeepd1 hexaware | Medium | In Progress | 2026-07-16 19:00 | 2026-07-20 14:13
I-071320 | TTC_ITO_DIGITAL_L3_PAYMENTGATEWAY |  | PaymentGateway-prod-Enrollment-Microservice-Exceptions | pradeepd1 hexaware | Medium | In Progress | 2026-07-16 19:00 | 2026-07-17 18:10
I-071225 | TTC_ITO_DIGITAL_NOCL1.5 |  | PaymentGateway-prod-API-5XXErrors | veneshg hexaware | Medium | In Progress | 2026-07-17 13:42 | 2026-08-05 12:33
I-070741 | TTC_ITO_DIGITAL_NOCL1.5 |  | PaymentGateway-prod-API-5XXErrors¦FRI and Nequi | SadhuR hexaware | Medium | In Progress | 2026-07-15 03:25 | 2026-08-05 12:33
I-070467 | TTC_ITO_DIGITAL_NOCL1.5 |  | PaymentGateway-prod-API-5XXErrors | TetaliK hexaware | Medium | In Progress | 2026-07-15 11:24 | 2026-08-05 12:37
I-070404 |  |  | Hi | AnandM4 hexaware | Medium | New | 2026-07-15 10:52 | 2026-07-15 10:53
I-070395 |  |  | PaymentGateway-prod-Delete-Payment-Tokens-Identifier-Exceptions | pradeepd1 hexaware | Medium | New | 2026-07-15 08:00 | 2026-07-15 10:46
I-070385 |  |  | PaymentGateway-prod-RDS-VolumeReadIOPs | Pammi Reddy | Medium | New | 2026-07-14 00:30 | 2026-07-15 10:42
I-070383 |  |  | PaymentGateway-prod-RDS-VolumeReadIOPs | Pammi Reddy | Medium | New | 2026-07-15 01:14 | 2026-07-15 10:40
I-070379 |  |  | PaymentGateway-prod-RDS-VolumeReadIOPs | Pammi Reddy | Medium | New | 2015-07-26 01:14 | 2026-07-15 10:38
I-070331 |  |  | PaymentGateway-prod-RDS-VolumeReadIOPs | Pammi Reddy | Medium | New | 2015-07-26 01:14 | 2026-07-15 10:06
I-070326 |  |  | PaymentGateway-prod-RDS-VolumeReadIOPs | Pammi Reddy | Medium | New | 2015-07-26 01:14 | 2026-07-15 10:02
I-070257 |  |  | PaymentGateway-prod-RDS-VolumeReadIOPs | Pammi Reddy | Medium | New | 2015-07-26 01:14 | 2026-07-15 09:26
I-070248 |  |  | PaymentGateway-prod-RDS-VolumeReadIOPs | Pammi Reddy | Medium | New | 2015-07-26 01:19 | 2026-07-15 09:24
I-070243 |  |  | PaymentGateway-prod-RDS-VolumeReadIOPs | Pammi Reddy | Medium | New | 2015-07-26 01:19 | 2026-07-15 09:20
I-070238 |  |  | PaymentGateway-prod-RDS-VolumeReadIOPs | Pammi Reddy | Medium | New | 2015-07-26 01:19 | 2026-07-15 09:17
I-070235 |  |  | PaymentGateway-prod-RDS-VolumeReadIOPs | Pammi Reddy | Medium | New | 2015-07-26 01:19 | 2026-07-15 09:15
I-070232 |  |  | PaymentGateway-prod-RDS-VolumeReadIOPs | Pammi Reddy | Medium | New | 2015-07-26 01:19 | 2026-07-15 09:14
I-069796 | TTC_ITO_DIGITAL_NOCL1.5 |  | tigo-cognito-prod-master-Monitoring-6I7LSTA3KZJH-LambdaErrors-27JT0HGYTAIS¦TigoID-Event-Processor-prod | veneshg hexaware | Medium | In Progress | 2026-07-15 01:55 | 2026-08-05 13:22
I-069631 | TTC_ITO_DIGITAL_L3_DAR |  | tigo-cognito-prod-master-Monitoring-6I7LSTA3KZJH-LambdaThrottles-T4BHZQAJD6PY | pradeepd1 hexaware | Medium | In Progress | 2026-07-14 03:00 | 2026-07-15 05:13
I-069597 | TTC_ITO_DIGITAL_NOCL1.5 |  | tigo-cognito-prod-master-Monitoring-6I7LSTA3KZJH-BillingSystemGetAccountsAPITimeoutErrorAlarm-1PCEMSDTPMP30¦EXTERNAL-APIS:BILLING-SYSTEM-GET-ACCOUNTS-API-TIMEOUT | SadhuR hexaware | Medium | In Progress | 2026-07-14 03:00 | 2026-08-05 13:23
I-069567 | TTC_ITO_DIGITAL_NOCL1.5 |  | PaymentGateway-prod-API-5XXErrors¦Nequi | veneshg hexaware | Medium | In Progress | 2026-07-14 05:30 | 2026-08-05 13:27
I-068899 | TTC_ITO_DIGITAL_NOCL1.5 |  | PaymentGateway-prod-API-5XXErrors | veneshg hexaware | Medium | In Progress | 2026-07-10 19:54 | 2026-08-05 13:27
I-068867 | TTC_ITO_DIGITAL_NOCL1.5 | Imrankhajamohiyoddinv hexaware | PaymentGateway-prod-RDS-ActiveTransactions | veneshg hexaware | Medium | In Progress | 2026-07-10 13:58 | 2026-08-05 13:28
I-068861 | TTC_ITO_DIGITAL_L3_DAR | akashg hexaware | tigo-cognito-prod-master-Monitoring-6I7LSTA3KZJH-LambdaErrors-27JT0HGYTAIS | TetaliK hexaware | Medium | In Progress | 2026-07-10 12:21 | 2026-07-10 03:20
I-068529 | TTC_ITO_DIGITAL_NOCL1.5 |  | PaymentGateway-prod-RDS-ActiveTransactions | veneshg hexaware | Medium | In Progress | 2026-07-09 17:39 | 2026-08-05 13:29
I-068518 | TTC_ITO_DIGITAL_L3_DAR | khajamohiyoddinv hexaware | PaymentGateway-prod-RDS-VolumeReadIOPs | veneshg hexaware | Medium | In Progress | 2026-07-09 15:46 | 2026-07-09 05:44
I-035125 | TTC_ITO_DIGITAL_L3_DAR |  | tigo-cognito-prod-master-Monitoring-6I7LSTA3KZJH-LambdaThrottles-T4BHZQAJD6PY | pradeepd1 hexaware | Medium | In Progress | 2026-07-08 19:45 | 2026-07-08 16:31
I-034913 | TTC_ITO_DIGITAL_NOCL1.5 |  | tigo-cognito-prod-master-Monitoring-6I7LSTA3KZJH-BillingSystemGetAccountsAPITimeoutErrorAlarm-1PCEMSDTPMP30 | veneshg hexaware | Medium | In Progress | 2026-07-08 20:44 | 2026-08-05 13:29
I-034855 | TTC_ITO_DIGITAL_L3_DAR | akashg hexaware | tigo-cognito-prod-master-Monitoring-6I7LSTA3KZJH-DARApiGateway4XXErrorAlarm-1RU6CTB3HN9ZJ | veneshg hexaware | Medium | In Progress | 2026-07-08 15:56 | 2026-07-08 07:38
I-033685 | TTC_ITO_DIGITAL_NOCL1.5 |  | tigo-cognito-prod-master-Monitoring-6I7LSTA3KZJH-OtpApiGateway4XXErrorAlarm-KCC0X1UFXS1F¦¦INCORRECT-OTP | veneshg hexaware | Medium | In Progress | 2026-07-04 03:20 | 2026-08-05 13:31
I-033296 | TTC_ITO_DIGITAL_NOCL1.5 |  | tigo-cognito-prod-master-Monitoring-6I7LSTA3KZJH-DARApiGateway5XXErrorAlarm-13T4WI2OP8WG1 | veneshg hexaware | Medium | In Progress | 2026-07-03 04:13 | 2026-08-05 13:32
I-033229 | TTC_ITO_DIGITAL_NOCL1.5 |  | tigo-cognito-prod-master-Monitoring-6I7LSTA3KZJH-DARApiGateway4XXErrorAlarm-1RU6CTB3HN9ZJ | veneshg hexaware | Medium | In Progress | 2026-07-03 02:43 | 2026-08-05 13:33
I-032815 | TTC_ITO_DIGITAL_NOCL1.5 |  | PaymentGateway-prod-API-5XXErrors | pradeepd1 hexaware | Medium | In Progress | 2026-07-01 11:00 | 2026-08-05 13:34
I-017386 | TTC_ITO_DIGITAL_NOCL1.5 |  | tigo-cognito-prod-master-Monitoring-6I7LSTA3KZJH-BillingSystemGetAccountsAPITimeoutErrorAlarm-1PCEMSDTPMP30 | veneshg hexaware | Medium | In Progress | 2026-06-26 16:24 | 2026-08-05 13:35
I-017366 | TTC_ITO_DIGITAL_NOCL1.5 |  | tigo-cognito-prod-master-Monitoring-6I7LSTA3KZJH-DARApiGateway5XXErrorAlarm-13T4WI2OP8WG1 | TetaliK hexaware | Medium | In Progress | 2026-06-26 12:28 | 2026-08-05 13:36
I-016676 | TTC_ITO_DIGITAL_NOCL1.5 |  | PaymentGateway-prod-API-5XXErrors | veneshg hexaware | Medium | In Progress | 2026-06-24 13:50 | 2026-08-05 13:43
I-016241 | TTC_ITO_DIGITAL_NOCL1.5 |  | tigo-cognito-prod-master-Monitoring-6I7LSTA3KZJH-DARApiGateway5XXErrorAlarm-13T4WI2OP8WG1 | pradeepd1 hexaware | Medium | In Progress | 2026-06-23 02:33 | 2026-08-05 13:45
I-015348 | TTC_ITO_DIGITAL_NOCL1.5 |  | PaymentGateway-prod-API-5XXErrors¦qrm | SadhuR hexaware | Medium | In Progress | 2026-06-18 18:15 | 2026-08-05 13:48
I-015171 | TTC_ITO_DIGITAL_L2_MOBIQUITY |  | PaymentGateway-prod-Event-Message-Processor-Exceptions | veneshg hexaware | Medium | In Progress | 2026-06-18 20:57 | 2026-06-19 09:30
I-014644 | TTC_ITO_DIGITAL_NOCL1.5 |  | tigo-cognito-prod-master-Monitoring-6I7LSTA3KZJH-DARApiGateway5XXErrorAlarm-13T4WI2OP8WG1¦EXTERNAL-APIS:BILLING-SYSTEM-GET-ACCOUNTS-API-TIMEOUT | SadhuR hexaware | Medium | In Progress | 2026-06-16 17:15 | 2026-08-05 13:49
I-014178 | TTC_ITO_DIGITAL_NOCL1.5 |  | tigo-cognito-prod-master-Monitoring-6I7LSTA3KZJH-DARApiGateway4XXErrorAlarm-1RU6CTB3HN9ZJ¦ /v4/trusted/auth/magic-links¦403 | SadhuR hexaware | Medium | In Progress | 2026-06-15 10:30 | 2026-08-05 13:49
I-014171 | TTC_ITO_DIGITAL_NOCL1.5 |  | tigo-cognito-prod-master-Monitoring-6I7LSTA3KZJH-DARApiGateway5XXErrorAlarm-13T4WI2OP8WG1 | pradeepd1 hexaware | Medium | In Progress | 2026-06-16 01:55 | 2026-08-05 13:50
I-012923 | TTC_ITO_DIGITAL_NOCL1.5 |  | PaymentGateway-prod-API-5XXErrors¦qrm | SadhuR hexaware | Medium | In Progress | 2026-06-10 09:50 | 2026-08-05 13:55